## Timeline
Month | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
Task | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01
Intership | bar: 2017-02-01 to 2017-04-01
Institutions final draft | bar: 2016-12-01 to 2017-01-01
Institutions submission | bar: 2017-02-01
Romania final draft | bar: 2017-05-01
Romania submission | bar: 2017-06-01
Zambia PGR modelling complete | bar: 2017-01-01 to 2017-06-01
Zambia PGR first paper draft | bar: 2017-07-01
Zambia PGR final draft and submission | bar: 2017-07-01 to 2017-09-01
UK diversity indicator method design | bar: 2016-12-01 to 2017-01-01
UK diversity data analysis | bar: 2017-05-01 to 2017-07-01
UK diversity first paper draft | bar: 2017-08-01 to 2017-09-01
UK diveristy final paper draft & submission | bar: 2017-10-01 to 2017-12-01
IMAGE Ex-situ questionaire design | bar: 2017-05-01 to 2017-07-01
IMAGE Ex-situ questionaire data analysis | bar: 2017-09-01 to 2017-11-01
IMAGE Ex-situ paper first draft | bar: 2017-12-01 to 2018-01-01
IMAGE Ex-situ paper final draft and submission | bar: 2018-02-01 to 2018-03-01
Thesis writing draft | bar: 2018-04-01
Thesis final draft | bar: 2018-05-01
Thesis review & final submission | bar: 2018-06-01
Note on A1: Warwick Wainwright: Includes extra 3 months funding from internship Must submit by Sept 2018
Note on A3: Warwick Wainwright: This is pending EWR board meeting - subject to change